## RCA
| 2022/12/8 Cephas | 2023/1/25 MHI | 2023/1/31 MOM of Cephas&MHI | 2023/2/08 MHI
| 1. Missing 2 bolts - As you can see from the left photo, 4 bolts should be connected to Top flange originally . However, only one bolt is connected to the flange and two bolts are missed and one bolt is loosen. - As follow the video that you sent, you can see there is a vibration. - The estimated reason is that it is assumed that the disc repeated a long time due to vibration, and the bolt was slowly loosened due to the vibration. | Your observation is fully NOT Accepted. Our question is the cause of vibration itself. Please analyze the reason for the "estimated disc repeated" situation. Disc must be stable. We assume Cephas's 1. the faulty assembly 2. anything associated with manufacturing tolerance (e.g. bolt tightning was not proper) As requested before, please provide inspection report of bolt tightening and photos before shipping. | We had fully complied with the work process during the prodution process including assembly. For your more easy understanding, Please See the traveler sheet for this valve. You could figure out that this valve was produced by complying to internal production requirements. (See attached Reference 1-1) | 1. Reference 1-1 does not have any indication of bolt tightening to the required extent. No evidence photos received in support of your saying. 2. Is it that Cephas do not match mark by marker pen/paint for the tightening confirmation before shipment?. Please adopt from now as the future prevention measure (improvement measure). This shall apply to all bolting connections. Please confirm. | 고객 : 토크쪼을떄, 사진찍어달라. 볼트랑 바디 사진을 찍어서 쪼은거를 확인할수있게.. 도장후에도 마크 표시가 있어야하는대.. 어케? 작업하기전 찍어야되는대, 하고나서 찍으면 의미가 없음 트레블러시트에 토크값을 입력을 하기에, 일일이 추가적으로 마킹하는거는 대응이힘들다 | 내용은 이해했지만, 추가적으로 마킹하는거는 대응이 힘들다
| 2. Disc damages ( both side) It is estimated that TEC 7 (waterproofing stuff), which was used as a Lifthole finishing process when we worked in 2020, has been removed over time by vibration due to irregular fluid movement. | Please describe any improved adhesion material had been used. We could not understand the countermeasures to this known issue. | we already improved the lift hole finishing process. Please find the attached latest lift hole finishing process(only for korean version). (see attached Reference 1-2) | Is this improved measure applied in this project?. Is there a mean to confirm it by any supporting document. If in this project, you had already improved the adhesion process, then does this mean that there is no further improvement possible?. Could you please share adhesion test report /relevant document for this improved adhesion process. | 어느프로젝트부터 적용? 적용시점확인필요 | 적용시점 확인 지피디 프로젝트는 전량 개선된 조치가 반영되었다. 부착력테스트를 하였고 jawa ? 건에도 적용하였다. 첨부자료 참고해라,
| 3. Inrush of Water in the Gear Box As you can see the left photos , it is estimated that there was a friction between the seat and the disc . Because of that, water has flowed in little by little through the worn body seat for a long time. | The photo does not show the disc seating area so that we could not understand the mechanism of damage by these photos. Please explain with associated drawing for our better understanding regarding your estimation sounds like "rubbing movement" or "the rubber part was torn away". In general seat and disc shall have proper mating during valve closing so it would be natural for friction to occur. | See attached Reference 1-3 | a) We do not understand the meaning of irregular flow. Do you mean pulsuating flow like some start/stop or vortex flow?. b)How do you think such irregular flow can occur? c) How can we prevent?. d)Does Cephas have any prior similar experience in which similar damaged occurred due to irregular flow and concluded a fool proof countermeasure?. | 1. 불규칙한 흐음.. 터블런스? 맥동은 펌프쪽 불규칙한 흐름때문에 생김. 정확하진 않지만 볼텍스, 터블런스 플로우같다.? 2. 불규칙한유체가 밸브에 영향을 주는 거 같다. 3. 라인에서 진동이 발생한다면 | a) 볼텍스, 터블런스 플로우다. 발생한 이유는 모르겠고, 추청을 할수있지만 단정지을수느 없다 2) 알수없다. 3) 와류나 난류에 의해 발생한 것으로 보이며, 궤도에 의해 흔들림을 최소화하는( 감소시키는 ) 방향을 추천. 80-85% 오픈상태에서 사용하기를 권장한다 4) 지난프로젝트에서 동일한 현상이 발생해서 c와 같이 조취해서 개선된 경험이 있다
↑Key Gorrove & Key | 4. Gap between key and stem (Due to the vibration, the shape of Key Groove is transformed) - Stem Key dimension in the drawing :20mm - Actual size tolerance : +0, -0.043) 1) Upper part of the insertion part : 20.5 mm 2) Lower part of the insertion part: part:20.0 mm 3) Key dimension is same as the dimension of drawing. | Explanation is not understandable for us. Please provide the said "drawing" with dimention and actual. We guess the gap (stem key and key slot?) has been increased due to vibration then where the metal had been worn out? Not breakage? #Please improve the readability. | There is only one key, so it seems that there is a crack in the inside corner of key home from the force applied to that side. As you can see from the 3.1 Material Certificate for Stem, that passed the UT test were used. (see attached Reference 1-4) | We note that there was no crack in stem before shipping.
| Due to the vibration, the shape of Key Groove is transformed - Please refer to the photo of stem key hole after disassembling (Please see the Inside Body). - There was a crack of Stem key hole. (Please refer to the yellow mark) | Based on your explanation we could conclude that the base reason that shaft had crack failure from the beginning (material defect) which caused the key slot to give more space for key to slide, which in turn caused the vibration of the valve shaft.
| (Due to the vibration, the shape of Key Groove is transformed - This is a photo after performing NDE(PT) test. - As you can see in the photos on the left, there are clearly cracks being under pressure in one direction. - Based on the above information , it seems that the extension of the key hole and the valve received continuous force in one direction due to the irregular flow of fluid, as a section 1. As a result, it is estimated that the cracks occurred as the stem key groove was deformed. | Valve shall be designed for the flow variations which is the basic need. We do NOT fully agree with your "irregular flow" as the whole equipment including pump, pipe, support etc will also be damaged in case any abnormal vibration is caused by fluid flow, which is surely not the case. On the other hand, based on your experience how do you propose we can arrest the "irregular flow" to prevent the future reoccurrence. | We have a reference that the valve vibration or fluttering phenomenon would be quite reduced by adjusting the opening degree. (80~90 % opening, not 100%). So, we would like to recommend to apply with the adjustment of opening degree to 80% ~ 90% intead of 100% open. | This is first time we hear and we welcome even if it is late. However please confirm is this new finding or is applied in many projects and have resolved issues with irregular flow?. Is this countermeasure specific to this valve or generally applicable for all. If we decide to adopt, we need to insert as part of Site installation Instructions (OMM). Please check and confirm. |  | 위에 언급했듯이, 이전에 개선된 경험이 있다. 밸브에 상관없이 이러한 현상이 발생한 밸브에 대해서만 적용한다.
5. Rubber has a tear on the top - It is estimated that the top part of seat is worn and torn by friction due to continuous vibration of the disc and body seat for a long time -Like the upper part of the seat , trace of friction was found on the lower part of the seat.
This is water from the inside DISC | 6. Inrush of water in the Disc - It is estimated that there was a friction between the seat and the disc . Because of that, water has flowed in little by little through the worn body seat for a long time.
7. Well bonded with seat and body - As a result of disassembling and observing the body and seat, there is no trace of water inflow except for the part where the body and seat rub, and the traces of the bond are evenly applied. So it is judged that the seat bonding work of the valve is well done.
In summary 1. It is judged that the vibration of Disc caused by irregular fluid flow wa s transmitted through the Stem . It occurs deformation of the Stem Key Groo ve, cracks, damage to the Stem, shaking of the ge arbox and making the bolts loosen Due to the damage parts of the valve, we recommend change the all parts of the valve except for Body. 2. The parts to be replaced - All parts except for Motor and Body 3. Estimated time of re work - Around 4 months |  | Please see our above comments and study to the root cause adequately and propose proper countermeasures. Please check on the stem related NDE (UT) records of the shop and see if there were no original internal /surface defects on it which propagated over use. | There is no Photo before shipping. As you can see from the 3.1 Material Certificate for Stem, that passed the UT test were used. (See attached Reference 1-4) | Noted.
절차에 맞춰 작업을 하였으며, 이전에 보내준 트레블러시트에서 확인이가능하다
[5 empty] | 시간이 갈수록 갭이 만들어졌다고했음. 시트와 디스크 사이의 갭 시간이 지나니깐 마찰에 의해 닳아서 갭이 발생했다 디자인적으로 많이 사용해도, 문제가 없어야 하는거아니냐? (구조상 맞물려서 돌아가야하는거아니냐) 불규칙한 규칙에의해 한쪽으로 편모가 먼저? 물이 들어간게 먼저? -> 마모가 되서 물이 먼저들어갔따(마모가되면 물림량이 없어지니깐..) 디스크 시트가 마찰하면 갭이 발생하고 그 후에 물이 들어갔따 뷸규칙한 유체에 의한 잦은 진동과 마찰로 인해 마모가 발생했고, 그 후에 유체가 유입되어 진동이 발생. | 이 지점에서 마찰은 정상적이다. 다만, 배관의 불규칙한 진동(동영상에서 보이는 진동, 떨림) 으로 밸브에 영향을 주는 것은 비정상이다.
[5 empty] | 작동하는대 왜 시트데미지가 더 악화되냐? 손상된 상태에서 계속사용하면 시트데미지가 악화되는 것은 당연하다 밸브가 손상된 상태에서 조립을 했었따??????????? 불규칙한 유체 흐름에 의해, 디스크가 한쪽으로 쏠린상태에서, 잦은 작동으로….. | 위와 동일함
[5 empty] | 부쉬와 팩킹있으니, 팩킹부에서 씰링을 해줘야하기에.. 관련사진있으면. 굿 진동에 의해, 탑 리테이너볼트가 느슨해지고, 유체에 의해 부식이되었고 누수가 발생 | 첨부영상처럼, 잦은진동 및 떨림에의해 탑 리테이너 볼트가 풀려 씰링 역할을 하지 못하였다. 또한, 유체에 의해 부식 및 누수가 발생
①Direction that the
Stem is to rotate
②Direction that the Key home receives force
③Here is the linear Crack
Stem