## Sheet1
ITP for Valves
Sl No: | Inspection Test | Characteristics | Applicable Documents | Sampling | Record/Document | Manufacturer | Supplier | TPI
2.1 | Material Identification | Chemical/Mechanical/ hardness etc. Properties | Relevant Material Std./ TPI-KIPIC-05- Valves/As per KIPIC PO | 100% | Supplier MTC / Report / EN 10204-3.1 | H | R | R
2.2 | Heat Treatment | Temperature for Heat Treatment /Holding and Method of cooling | Relevant Material Std./ TPI-KIPIC-05- Valves | 100% | Heat Treatment report | H | R | R
2.3 | Inter Granular Corrosion | Stainless steel/ Alloy Steel | Practice E of ASTM 262 /Relevant Material Std./ TPI-KIPIC-05- Valves | 100% | IGC report | H | R | R
2.4 | All NDT test | For all cast Type, For Forged Type >=900 Class | Relevant Std./ TPI-KIPIC-05- Valves/As per KIPIC PO | 100% | NDT Report | H | R | R
2.5 | Microstructure/Grain Size | For Austenitic Stainless Steel | As per ASTM E112 and applicable ASTM Spec. | 100% | Test Report | H | R | R
2.6 | Solution Annealing | For Austenitic Stainless Steel | Relevant Std./ TPI-KIPIC-05- Valves/As per KIPIC PO | 100% | Test Report | H | R | R
2.7 | Hardness/ NACE requirement | Hardness test | NACE Std./PO requirement | 100% | HIC/SSC/relevant reports | H | R | R
2.8 | Ferrite | Ferrite test | PO requirement | 100% | Test Report | H | R | R
2.9 | Fire Safe Test | Fire Safe Test | PO requirement | 100% | Test Report | H | R | R
2.1 | Any Special Test Required | As mentioned in the P.O | PO requirement | 100% | Test Report | H | R | R
3.1 | Visual check/ Dimensional Check | defects free/ Finish/trim/Flow direction/Rubber lining/ and dimensional analysis | Rel. Dimensional Std./TPI-KIPIC-05- Valves,MSS-SP-55 | 100% | Visual/Dimensional Report | H | NA | 5 %-W 100%- R
3.2 | Spark Test/ Shore Hardness | Spark Analysis/Shore Hardness | PO requirement | 100% 5% | Spark /ShoreTest Report | H | NA | W
3.3 | Ultrasonic Flaw Detection/ Dilution Test | For weld Overlay Disbonding | PO requirement | 100% | Test Report | H | R | R
6 | Review WPS/PQR/WPQR/NDT Certificate | For all kind of valves | Rel. Std./TPI-KIPIC-05- Valves | 100% | All reports | H | R | R
7 | PMI for Body and Bonnet | Except CS | Rel. ASTM Std./TPI-KIPIC-05- Valves | 100% | PMI report/Stencil by TPI | H | H | 100% W for Body Bonnet R-PMI on Trim
8 | Thickness Check for the Body and Bonnet by the Vendor | For all kind of valves | Rel. ASTM Std./TPI-KIPIC-05- Valves | 100% | Thickness Check Report | H | H | W
9 | Witness Hydro/ Pneumatic/Seat test | 100% for Alloy steel/SS/NACE compliance (stamped)/10% for CS as per API 598 | Rel. Std./TPI-KIPIC-05- Valves./PO requirement | 100% | Test Report | H | R | W
11 | Packing and Marking | Spec, Heat No. Manf name, PMI stencil mark | ASTM A700/as per PO | 100% | Attach Photo | P | W | W
11.2 | Color coding | Color coding | Annexure-III/Color Coding/TPI-KIPIC-05- Valves | 100% | Attach Photo | P | W | W
16 | Final Inspection Report | Documentation | TPI-KIPIC-05- Valves | 100% | All reports | H | R | R/A
Legends: | H- HOLD, P-PERFORM, R- REVIEW, W-WITNESS, A-APPROVE