## SV REPORT
Supervision Report for Van Phong Project
Site - Van Phong, Vietnam
Supervision Date : 2023.03.22~2023.03.23
Supervisors : Mr. Namsik Yoon, Mr. Sugun Lee (Cephas)
1. Subject - Inspection for 2 valves
We received a request from Toshiba to solve their current problem with two of the valves at the site. The current status was |  |  |  | 도시바로 부터 납품한 밸브 2대에 문제가 있다는 연락을 접수하였으며, 시퍼스 기술자가 사이트에 방문하여 점검해달라는 요청을 접수하였습니다.
when the valves were fully closed by handle, the valve disc exceeded fully close point and there were the gap between valve disc |  |  |  | 현 상황으로는 밸브를 핸들로 완전히 닫을 때, 디스크가 완전히 닫히는 지점을 초과하고 밸브 디스크와 바디시트 사이에 틈이 있다고 합니다.
and body seat. So, Cephas supervisors went to the Van Phong site in Vietnam to perform an inspection on 2 valves. |  |  |  | 이에, 시퍼스 SV는 사이트로 파견되어 밸브 2대를 점검하였습니다.
(Tag NO. 10LBR20 AA201, 10LBR30 AA201)
2. Site Investigation & Inspection schedule
| <TAG NO.10LBR20 AA201> |  | <TAG NO.10LBR30 AA201>
Mar 22th - Cephas supervisors received safety education for the work site and performed an Inspection based on
the Check Sheet for Tag no.10LBR20 AA201.
Mar 23th - Performed an inspection based on the Check Sheet for Tag no.10LBR30 AA201.
3. Action
<TAG NO.10LBR20 AA201>
1) Did the operator wear the protective gear for safety?
-> CEPHAS : The Cephas SV wore the protective gear while inspecting the valves.
2) Check the Orientation of the Valve / Check to see the Retainer ring bolt has been loosened /
Check the stop bolt's status of release.
-> CEPHAS : Cephas Supervisors checked the conditions of the valve orientation, the retainer ring bolt and the stop bolt.
There were no problems.
3) Open the disc about 10% (check for smooth operation as well as any noises while operating.)"
-> CEPHAS : No sound was made and the valve disc moved smoothly while operating the valves.
4) Check whether there is any damage to the Disc and the Seat."
-> CEPHAS : There was no damage to the seat and disc.
5) Close the disc completely til it is the" fully close" position and check the gearbox."
-> CEPHAS : Cephas supervisors set the closing position of Disc. After fully closing the valves, the Cephas SV checked
the gearbox indicator position and marked the position with a white marker.
6) Seat Leak Test. (Check the movement of the gear box and the Indigator when pressurized.)"
-> CEPHAS : After filling with water in Pipeline, the site engineer performed the leak test. There was no problem.
7) When operating the motor, loosen the stop bolt by turning it fully around about 3 times and secure the nut firmly.
-> CEPHAS : Cephas supervisors adjusted the stop bolt by loosening
<TAG NO.10LBR30 AA201>
1) Did the operator wear the protective gear for safety?
-> CEPHAS : The Cephas SV wore the protective gear while inspecting the valves.
2) Check the Orientation of the Valve / Check to see the Retainer ring bolt has been loosened /
Check the stop bolt's status of release.
-> CEPHAS : Cephas Supervisors checked the conditions of the valve orientation, the retainer ring bolt and the stop bolt.
There were no problems.
3) Open the disc about 10% (check for smooth operation as well as any noises while operating.)"
-> CEPHAS : No sound was made and the valve disc moved smoothly while operating the valves.
4) Check whether there is any damage to the Disc and the Seat."
-> CEPHAS : There was no damage to the seat and disc.
5) Close the disc completely til it is the" fully close" position and check the gearbox."
-> CEPHAS : Cephas supervisors set the closing position of Disc. After fully closing the valves, the Cephas SV checked
the gearbox indicator position and marked the position with a white marker.
6) Seat Leak Test. (Check the movement of the gear box and the Indigator when pressurized.)"
-> CEPHAS : After filling with water in Pipeline, the site engineer performed the leak test. There was no problem.
7) When operating the motor, loosen the stop bolt by turning it fully around about 3 times and secure the nut firmly.
-> CEPHAS : Cephas supervisors adjusted the stop bolt by loosening
4. CONCLUSION
The setting method for Manual valve and Motor Valve is different. |  |  |  | MANAUL 타입과 MOV 타입 밸브의 셋팅하는 방법은 다릅니다. 당사에서는 MOV 타입의 밸브를 납품하였지만
Cephas supplied the valve that already set according to Motor operator but it confirmed that site workers operated the valve manually |  |  |  | 사이트에서는 전기가 연결되지 않은 상태에서 밸브를 매뉴얼로 작동하였고 오버클로즈 현상 및 디스크와 바디시트 사이에 갭이 발생한 것으로 확인하였습니다.
without electric power and it made the disc exceeded fully close point and there were the gap between valve disc and body seat. |  |  |  | 이에 대해, 시퍼스 SV는 체크리스트에 따라 모든 점검(시트, 리테이너 볼트, 작동상태 등)을 완료하였으며,
Upon this realization, cephas supervisors performed the inspection based on the check sheet which included :seat, retainer bolt, |  |  |  | MOV 셋팅을 하는 과정에서 현장 담당자에게 조세볼트 셋팅 방법에 대해 충분히 인지시켰습니다.
operation and etc. While new setting the MOV valve, we explained how to set the stop bolt and the site managers are fully aware of it. |  |  |  | 그 후, 배관에 물을 채워 테스트를 하였고, 이상이 없음을 확인하였습니다.
Finally, site manager filled with water into the pipeline to perform the leak test and there was no problem.
(Cephas Pipelines Corp.)